|  | Office of Information Resources Management Office of the Assistant Secretary for Management and Budget Department of Health and Human Services |  |  |
| --- | --- | --- | --- |
|  | HHS IRM Policy for Capital Planning and Investment Control |  |  |
|  | January 8, 2001 |  |
|  | Project: | HHS IRM Policy |  |
|  | Document Number: | HHS-IRM-2000-0001 |  |

# TABLE OF CONTENTS

1.	Purpose	3

2.	Background	4

3.	Scope	5

4.	Policy	6

4.1.	General Policy	6

4.2.	Requirements for Departmental ITIRB Review	7

4.3.	Criteria for Departmental ITIRB Review	7

4.4.	Products for ITIRB Review	8

4.5.	OPDIV Capital Planning and Investment Control (CPIC)/ITIRB Requirements	8

5.	Roles and Responsibilities	10

5.1.	The HHS Chief Information Officer (CIO)	10

5.2.	The Deputy Assistant Secretary for Information Resources  Management	10

5.3.	The OPDIV CIOs	10

5.4.	The Desk Officers	11

5.5.	The HHS ITIRB	11

6.	Applicable Laws/Guidance	13

7.	Information and Assistance	13

8.	Effective Date/Implementation	13

9.	Approved	13

Glossary	13

Figure A: ITIRB Review Process with Required Products	18

Figure B: Capital Planning and Investment Control Project Summary	19

Figure C: HHS Capital Planning and Investment Control Checklist	23

Appendix A: Legislative Requirements and Guidance for Capital Planning and Investment Controls	26

# Purpose

This circular establishes the policies and responsibilities for performing information technology capital planning and investment control (CPIC) processes throughout the Department of Health and Human Services (HHS).

.

# Background

Investments in information technology (IT) can dramatically enhance organizational performance.  When carefully managed, IT becomes a critical enabler to improve business processes, makes information widely available to all that can benefit from it, and reduces the cost of providing essential Government services.  As IT rapidly evolves, the challenge of realizing its potential benefits also becomes much greater.

Congress and OMB have clearly stated that each executive agency must actively manage its IT program to provide assurances that technology expenditures are necessary and will result in demonstrated improvements in mission effectiveness and customer service.  The Clinger-Cohen Act (CCA) legislatively mandates the prudent management of IT investments.

One key goal of the CCA is for agencies to develop policies and processes that will result in implementation of systems at acceptable costs, within reasonable and expected time frames, and contribute to tangible, observable mission performance.  These processes must be institutionalized throughout the organization, must ensure compliance with the Department’s Information Technology Architecture (ITA), and will be used for all IT-related decisions.

# Scope

This policy applies to all Departmental system development, maintenance efforts, and infrastructure computing resources at all levels of sensitivity, whether owned and operated by HHS, or operated on behalf of HHS.

This policy supersedes Circular No. IRM - 201, Capital Planning and Investment Control, dated March 1999.

# Policy

## General Policy

HHS is required to conform with the Clinger-Cohen Act of 1996 to which this policy conforms.  Specifically Section 5122 of the Clinger-Cohen Act of 1996 (CCA), which states the following:

SEC. 5122. CAPITAL PLANNING AND INVESTMENT CONTROL.

(a) DESIGN OF PROCESS- In fulfilling the responsibilities assigned under section 3506(h) of title 44, United States Code, the head of each executive agency shall design and implement in the executive agency a process for maximizing the value and assessing and managing the risks of the information technology acquisitions of the executive agency.

(b) CONTENT OF PROCESS- The process of an executive agency shall--

(1) provide for the selection of information technology investments to be made by the executive agency, the management of such investments, and the evaluation of the results of such investments;

(2) be integrated with the processes for making budget, financial, and program management decisions within the executive agency;

(3) include minimum criteria to be applied in considering whether to undertake a particular investment in information systems, including criteria related to the quantitatively expressed projected net, risk-adjusted return on investment and specific quantitative and qualitative criteria for comparing and prioritizing alternative information systems investment projects;

(4) provide for identifying information systems investments that would result in shared benefits or costs for other Federal agencies or State or local governments;

(5) provide for identifying for a proposed investment quantifiable measurements for determining the net benefits and risks of the investment; and

(6) provide the means for senior management personnel of the executive agency to obtain timely information regarding the progress of an investment in an information system, including a system of milestones for measuring progress, on an independently verifiable basis, in terms of cost, capability of the system to meet specified requirements, timeliness, and quality.

The Clinger Cohen Act requires that capital investments related to IT must be reviewed on an annual basis by the Department CIO.  To accomplish this, each OPDIV shall establish an Information Technology Investment Review Board (ITIRB) and an ITIRB process in accordance with this policy.  Regardless of the size, complexity, risk, or cost, the same process shall be followed. All OPDIV expenditures shall follow the process shown in Figure A, “ ITIRB Review Process with Required Products”.  However, based on the size, complexity, risk, cost and phase of the IT investment, the granularity of the detail of the IT investment review, analysis, and documentation will vary.  The highest priority IT investments will then be further reviewed by the Department CIO to ensure CCA compliance and ensure that HHS is effectively managing its IT costs and risks associated with HHS mission and infrastructure.  For investments and expenditures that meet or exceed the criteria below, Department level reviews shall be required.

## Requirements for Departmental ITIRB Review

All OPDIV expenditures that meet any of the criteria Section 4.3 shall provide a Capital Planning and Investment Control Project Summary (see Figure B, “Capital Planning and Investment Control Project Summary”) to the Office of Information Resources Management for review.  This summary is based on the results of documentation from the OPDIV ITIRB review.  OIRM shall review the summary, and based on size, complexity, cost and risk factors, OIRM shall then determine whether the OPDIV ITIRB is sufficient to serve as the Department ITIRB for review or whether a Department ITIRB is required.  Wherever possible, existing documentation shall be used to meet the requirement for providing documentation to the OPDIV ITIRB and the Department ITIRB.  In making this assessment, OIRM may request, and the OPDIV shall provide, additional documentation.  In addition, each OPDIV CIO shall provide and certify annually an inventory of all current and future initiatives that contain an IT component.

## Criteria for Departmental ITIRB Review

All IT expenditures meeting either of the criteria below shall be presented to the Departmental Information Technology Investment Review Board (ITIRB):

(1) Crosscutting systems and technology that may affect more than one Operating Division (OPDIV) at any level of resources.

(2) Systems that meet the OMB definition of “major information system,” which means an “information system that requires special management attention because of its importance to an agency mission; its high development, operating or maintenance costs; or its significant role in the administration of agency programs, finances, property, or other resources.”

The Department CIO or Deputy Assistant Secretary for OIRM retains the discretion to direct that any specific system be brought to the Department ITIRB.

## Products for ITIRB Review

For all IT investments submitted to the Department ITIRB, the OPDIVs shall provide a business case and associated products including at least the following products.  At each stage in the ITIRB review process, as shown in Figure A, “ ITIRB Review Process with Required Products”, specific products are to be reviewed.

- A business need and high level requirements analysis that defines the specific need and requirements this system will fulfill, clearly demonstrates how the project supports the OPDIV and HHS strategic plans, business functions, and mission-critical functions, and HHS IT architecture.

- Return on investment (ROI) and cost-benefit/alternatives analysis in accordance with the HHS IRM Policy for Conducting Information Technology Alternatives Analysis, HHS-IRM-2000-0002.

(3) A risk assessment and mitigation plan.

(4) A technical strategy and plan.

(5) An economic sensitivity analysis to assess economic impacts due to changes in key variables.

- A performance measurement plan that includes an identification, definition, collection and tracking plan.

- A spending and procurement plan, including Independent Verification and Validation (IV&V) and testing funds.

- A project plan, a schedule, and a work breakdown structure.

Each of the elements for a given stage must be addressed.  If they do not apply, the response shall state the reason for non-conformance. Each system meeting the requirement of Sections 4.2 or 4.3 shall be subject to the Departmental ITIRB at each review point shown in Figure A, “ ITIRB Review Process with Required Products”. For projects not subject to Departmental ITIRB review, the same review points shown in Figure A, “ ITIRB Review Process with Required Products”, shall be applied by the respective OPDIV, with products produced at the level of specificity appropriate to the size, complexity, cost and risk of the project.  Guidance for preparing these documents can be found in the attached guidelines.

## OPDIV Capital Planning and Investment Control (CPIC)/ITIRB Requirements

Each OPDIV shall establish and manage capital planning and investment control (CPIC) processes and ITIRB review structures in a manner consistent with the requirements of this policy, including Appendix A: Legislative Requirements and Guidance for Capital Planning and Investment Control. Requirements also include:

- compliance with the Department’s Enterprise Information Technology Architecture (ITA);

- coordination of IT investment reviews with Departmental budget timelines and documentation requirements;

- assurance that investments adhere to legislative requirements and best practices for security and privacy protection, including privacy impact assessments; and

- obtaining approval by the appropriate ITIRB of investments prior to approval of budgets by the Service and Supply Fund Board.

- obtaining appropriate ITIRB approval prior to obligation of funds for development of new IT systems meeting the criteria in Section 4.3; and

- submit an OMB Exhibit 53, “Agency IT Investment Portfolio” and any necessary OMB Circular A-11 forms 300B, “Capital Asset Plan and Justification” for the next available budget cycle submission.

# Roles and Responsibilities

## The HHS Chief Information Officer (CIO)

The CIO is responsible for providing advice and assistance to the Secretary and other senior management personnel, to ensure that information technology is acquired and information resources are managed for the agency in a manner that implements the policies and procedures of the CCA.  The CIO is also responsible for developing, maintaining, and facilitating the implementation of a sound and integrated information technology architecture, and promoting the effective and efficient design and operation of all major information resources management procedures and processes for the agency, including improvements to work processes of the agency.

The CIO is a member of the Federal CIO Council, and chairs the HHS CIO Council.  The CIO also chairs the HHS ITIRB.  The HHS CIO is the final approval authority for the HHS ITIRB.

## The Deputy Assistant Secretary for Information Resources  Management

The Deputy Assistant Secretary for Information Resources Management (DASIRM) is the vice chair for the HHS ITIRB.  The DASIRM shall ensure that HHS IT investments satisfy the CCA, effectively and efficiently support mission requirements, meet strict efficiency and performance criteria, and conform to the HHS architecture.  OIRM will serve as the executive secretariat, preparing agendas, scheduling meetings, and taking notes and minutes of the proceedings for distribution to the CIO and the Deputy CIO, the OPDIVs, and OPDIV staff.

The DASIRM formulates and issues policy, requirements, and procedural guidance for OPDIV use in conducting ODPIV ITIRBs and in preparing for Departmental ITIRB evaluations, reviews, documentation of status, and investments in HHS mission critical systems.

The DASIRM is the Deputy CIO, is a member of the Federal CIO Council, and is the vice chair of the HHS CIO Council.  The DASIRM formulates the Department’s IT goals and strategies for defining measures of success for assessing and evaluating IT use and reporting the status of the Department’s IT programs.

## The OPDIV CIOs

The OPDIV CIOs shall be responsible for performing capital planning and investment control (CPIC) for their OPDIV consistent with current legislation and HHS policy, including establishment of an OPDIV ITIRB.  The OPDIV CIO is responsible for performing functions similar to those of the HHS CIO and the HHS DASIRM. The OPDIV CIOs are members of the HHS ITIRB. The OPDIV CIO shall provide material to support system justification to the HHS Deputy CIO and the pertinent desk officer in advance of an ITIRB meeting.

Annually, the OPDIV CIO shall provide and certify an inventory of all current and future initiatives that contain an IT component.

## The Desk Officers

The OIRM desk officers support the DASIRM in his or her role as the vice chair of the Departmental ITIRB and are the focal point for working with their OPDIVs on critical IT issues throughout the system life cycle. These issues include initiatives such as a single HHS ITA, security, systems development activities, CPIC processes, and Independent Verification and Validation (IV&V).  Each desk officer shall be responsible for having a thorough knowledge of his or her OPDIV and work collaboratively with the OPDIVs on CCA issues.

The desk officers shall request and receive documentation from their respective OPDIVs for designated IT investments.  The desk officers shall analyze the material provided to support the business case for the system, and make recommendations for action.  The OIRM desk officers are responsible for reviewing IT-related documents, OMB Form 300B and OMB Exhibit 53.  The desk officers may attend the Departmental and OPDIV ITIRB meetings for informational purposes.

## The HHS ITIRB

The HHS ITIRB has the responsibility and authority to review investments that meet the criteria established in Section 4, “Policy,” above.  The HHS ITIRB will meet at least quarterly to consider new IT system developments and upgrades, and to review the progress of the already approved IT development, upgrades, and operations.

The ITIRB shall consist of the CIO, the Deputy CIO, the OPDIV CIOs, and the Deputy Assistant Secretaries, Grants and Acquisition Management (OGAM), Finance (OF), Budget (OB), and Human Resources (HR).  Key OPDIV program managers may be invited to discussions affecting their programs.  The Deputy CIO, OPDIV CIOs and the ASMB Deputy Assistant Secretaries will attempt to reach consensus, and make recommendations for system approval, disapproval or other action (e.g., suggestions to improve the business case), to the HHS CIO.

The HHS ITIRB shall submit proposed results and recommendations of the ITIRB to the HHS CIO, who may accept, alter, or reject the ITIRB recommendations.

Specifically, the ITIRB members shall:

- Assess the candidate IT investment by reviewing the products specific to the current stage as shown in Figure C, “HHS Capital Planning and Investment Control Checklist”.

- Ensure that the proposed project is in conformance with the HHS ITA.

- Consider and recommend any necessary emergency system development or upgrade requests.

- Assess the adequacy of HHS information asset protection through the system’s information security (cyber and physical), and fraud and abuse detection mechanisms, consistent with Federal and Departmental security policy and guidance.

- Ensure that security controls and authentication tools to be deployed are consistent with the protection of personal privacy (i.e., medical records, human resource documents, and financial statements) as determined through privacy impact assessments.

- Evaluate already approved system development, upgrades, baseline operations and maintenance to ensure continued acceptable performance.

- Recommend continuation, termination of, or changes to, previously approved projects.

- Assess the CPIC processes for “lessons learned” at least annually.

- Establish and maintain systems compliance with Section 508 of the Workforce Investment Act of 1998.

# Applicable Laws/Guidance

See Appendix A, “Legislative Requirements and Guidance for Capital Planning and Investment Control.”

# Information and Assistance

Direct questions, comments, suggestions or requests for further information to the Deputy Assistant Secretary for Information Resources Management, (202) 690-6162.

# Effective Date/Implementation

The effective date of this policy is the date the policy is approved.

The HHS policies contained in this issuance shall be exercised in accordance with Public Law 93-638, the Indian Self-Determination and Education Assistance Act, as amended, and the Secretary’s policy statement dated August 7, 1997, as amended, titled “Department Policy on Consultation with American Indian/Alaska Native Tribes and Indian Organizations.”  It is HHS’ policy to consult with Indian people to the greatest practicable extent and to the extent permitted by law before taking actions that affect these governments and people; to assess the impact of the Department’s plans, projects, programs and activities on tribal and other available resources; and to remove any procedural impediments to working directly with tribal governments or Indian people.

# Approved

______/s/____________________	_01/08/01_

John J. Callahan				    DATE

Assistant Secretary for Management

and Budget

# Glossary

Activity - Identifies what needs to be done to achieve a stated mission or purpose, without addressing how it is to be accomplished.

Alternative Analysis - An evaluation of scenarios and design paths for meeting a general set of system design requirements described in a Business Need Document, or a specific technical/architectural issue.  This evaluation presents alternatives, which include assessments of current system functionality and design that may satisfy some of the requirements as well as the functionality that may impact the interfaces with other systems.  A set of evaluation criteria is used to weight the various alternatives against each other and provide a recommendation for the analysis.

Architecture - The organizational structure of a system or component (IEEE 90).

Baseline - A specification or product that has been formally reviewed and agreed upon, that thereafter serves as the basis for further development, and that can be changed only through formal change control authority.

Business Case – A structured proposal for a business need that serves as an investment decision package to improve business operations.  A business case consists of a business need, and a technical evaluation.

Business Need – Any request at a high or low level to improve, change, update, or add new systems that facilitate the agency’s missions, goals and objectives.

Business Need Document – A document is submitted by an individual or an organization.  This document describes a request for a system change, system improvement, or a new system and provides the information required by the engineering community to develop a change or a new system.

Capital Planning – A discipline used by management to reduce the risk and increase the return associated with making investments of capital assets.

Change Request – The change instrument used to identify changes affecting the functional baselines and cost, schedule, and contractual data associated with information systems baselines.  Change requests may also be used to identify changes from subordinate configurations that impact baselines outside their authority.

Enterprise – The entire agency and /or its components.

Impact Assessment – An analysis to determine the effect of a change to a current or new developmental system with the purpose of evaluating how the proposed change affects the target technical, cost, and schedule.

Information System – A discrete set of information technology, data, and related resources, such as personnel, hardware, software, and associated information technology services organized for the collection, processing, maintenance, use, sharing, dissemination or disposition of information.

Information Technology – Any equipment or interconnected system or subsystem of equipment, that is used in the automatic acquisition, storage, manipulation, management, movement, control, display, switching, interchange, transmission or reception of data or information by the agency. . For purposes of this definition, equipment is “used” by an agency whether agency uses the equipment directly or it is used by a contractor under a contract with the agency which (1) requires the use of such equipment or (2) requires the use, to a significant extent, of such equipment in the performance of a service or the furnishing of a product. Information technology includes computers, ancillary equipment, software, firmware and similar procedures, services (including support services), and related resources. It does not include any equipment that is acquired by a Federal contractor incidental to a Federal contract.

Investment Control – Management investment oversight activities to monitor projects under development and operational systems to ensure that the cost, risk, and performance criteria used to select the investments are being achieved.  Corrective actions and project continuation decisions are made based on periodic monitoring.

Infrastructure – A sub-structure or underlying foundation; the basic installations and facilities on which information systems depend (i.e., hardware platform, operating system, telecommunications).

Legacy System – An established computer system that is currently operational and supports existing business functionality.

Maintenance – The set of activities which result in changes to the originally accepted baseline product set, in order to keep the system functioning in an evolving, expanding user and operational environment.

Major IT System – A system that requires special management attention because of its importance to an agency mission; its high development, operating, or maintenance costs; or its significant role in the administration of agency programs, finances, property, or other resources. Large infrastructure investments (e.g. major purchases of personal computers or local area network improvements) should also be evaluated against these criteria.

Net Present Value –Net present value (NPV) analyses are used to compare investment alternatives that occur over multiple years.  Present Value requires that all quantifiable benefits and costs are brought back to current day dollar values, so that various alternatives can be compared directly.

Performance – The degree to which a system or component accomplishes its designated functions within given constraints, such as speed, accuracy, or memory usage (IEEE 90).

Phase – A level of the system life cycle that generally specifies major activities, products, reviews and organizations, roles and responsibilities; and that establishes the level of detail and establishes product accountability.

Pilot – The period of time, at a specific pilot site, when a system is delivered, installed, integrated, and tested in an actual production environment against customer requirements.

Pre-Coordination – Notification that a request is being considered for submission, but certain information is needed from stakeholders to determine whether the request will be submitted.

Process – an organized set of activities with defined inputs and outputs, performed to achieve a stated purpose.

Product – Anything used or produced to satisfy a need, for example, facilities, systems hardware, software, firmware, data, processes, materials, or services.

Program Area – A representation of customer organizations.

Program Management – The planning, organizing, directing, and controlling of the resources and schedules which coordinate the prioritization and sequencing of a collection of similar, or interdependent projects.

Release – A grouping of actual software and hardware upgrades, improvements, enhancements, replacements, new business, and information systems capabilities, as well as retirement of legacy systems.

Requirements Analysis - A problem-solving activity that involves studying the ways an organization currently retrieves and processes data to produce information, identifies any problem areas, and considers how the users’ needs might best be satisfied.

Requirements Management – The activities or processes that assess, refine, and prioritize business needs to address the requirements of the changing business environment, to establish and maintain an up-to-date understanding between business needs and the development organizations regarding the requirements to be addressed by the delivered product.

Return on Investment – Return on Investment (ROI) of the project shows how much the project benefits the organization in comparison to cost savings or cost avoidance.

Review – A formal evaluation procedure issued to determine the correctness of the products developed during a system life cycle phase.

Stakeholders – Individuals, organizations, review boards, and committees with vested interest in the result of a decision, process, review, or activity.

System  -  One or more of the following: (1) an integrated composite of people, products, and processes that provide a capability to satisfy a need or objective [MIL-STD-499B]; (2) an assembly of things or parts forming a complex or united as a whole; a collection of components organized to accomplish a specific function or set of functions; (3) an interacting combination of elements, viewed in relation to function [INCOSE95].  A system may be a product that is hardware only, hardware/software, software only, or a service.  The term “system” is used to indicate the sum of the products being delivered to the customers or users of the products. See also the definition of information system.

System Life Cycle – A structured development approach with defined activities, phases, products, and reviews providing a standard to support the development of systems from identification of a business need through implementation, operation, maintenance, and eventual retirement.

System Requirement – A function or characteristic of a system that is necessary, or the quantifiable and verifiable behaviors that a system must possess, and constraints that a system must work within to satisfy an organization’s objectives and solve a set of problems.

Technical Evaluation – Activities to appraise the technical solutions and associated costs and schedules presented by a customer.  The major activities include technical analysis on proposed solutions with cost and schedule, architecture impact analysis to determine the solution’s impact, and technical evaluation review presenting technical evaluation to stakeholders for approval.

# Figure A: ITIRB Review Process with Required Products

# Figure B: Capital Planning and Investment Control Project Summary

|  |  |  | Capital Planning and Investment Control Project Summary |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Agency |  |  |  |  |  |  |  |  |  |  |  |  |
| Bureau |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Owner |  |  |  |  |  |  |  |  |  |  |  |  |
| Executive Sponsor |  |  |  |  |  |  |  |  |  |  |  |  |
| Program Activity |  |  |  |  |  |  |  |  |  |  |  |  |
| Name of Project |  |  |  |  |  |  |  |  |  |  |  |  |
| Check One | New Project |  |  |  |  | Ongoing Project |  |  |  |  |  |  |
| Was this project approved by an Investment Control Board (or and Executive Review Committee)? |  |  |  |  |  |  |  |  | Yes |  | No |  |
| Is this project a financial management system? |  |  |  |  |  |  |  |  | Yes |  | No |  |
| If so, what percentage of the system is financial? |  |  |  |  |  |  |  |  |  |  | % |  |
| What percentage of the costs are for security? |  |  |  |  |  |  |  |  |  |  |  |  |
| SUMMARY OF SPENDING FOR PROJECT STAGES |  |  |  |  |  |  |  |  |  |  |  |  |
| (In Thousands) |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Prior Year-1 & Earlier | Prior Year | Current Year | Fiscal Year+1 | Fiscal Year+2 | Fiscal Year+3 | Fiscal Year+4 | Fiscal Year+5 | Outyears | Total |  |
| Planning |  |  |  |  |  |  |  |  |  |  |  |  |
| Est.Budget Authority |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Budget Authority |  |  |  |  |  |  |  |  |  |  |  |  |
| Outlays |  |  |  |  |  |  |  |  |  |  |  |  |
| Full Acquisition |  |  |  |  |  |  |  |  |  |  |  |  |
| Est. Budget Authority |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Budget Authority |  |  |  |  |  |  |  |  |  |  |  |  |
| Outlays |  |  |  |  |  |  |  |  |  |  |  |  |
| Total, sum of stages (excludes maintenance) |  |  |  |  |  |  |  |  |  |  |  |  |
| Est.Budget Authority |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Actual Budget Authority |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Outlays |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |
| Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |
| Est. Budget Authority |  |  |  |  |  |  |  |  |  |  |  |  |
| Actual Budget Authority |  |  |  |  |  |  |  |  |  |  |  |  |
| Outlays |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTALS |  |  |  |  |  |  |  |  |  |  |  |  |
| I. MISSION SUPPORT: Describe how the project supports the core/priority mission functions that need to be performed by the OPDIV/Bureau. List the organizations, components, or groups served by this effort. State the authority that entitles the agency to develop the project or whether the project implements a legislative requirement. |  |  |  |  |  |  |  |  |  |  |  |  |
| II. BUSINESS NEED: Provide a high level requirements or problem statement used to define the system design requirements, and define the scope of the problem. Identify the specific deficiency or need this project will fulfill and resulting profit or advancement what will be gained when the project is completed. |  |  |  |  |  |  |  |  |  |  |  |  |
| III. FINANCIAL AND ALTERNATIVE ANALYSES: Provide projections on the approach and schedule for completion. Identify the alternatives, including no action, and other COTS solutions, developmental solutions and any reasonable combination of hardware, software and migration/transition solutions. Briefly summarize the results from the cost analysis, schedule analysis and risk analysis for each alternative. Show how the project meets Government Performance and Results Act (GPRA) goals and the OPDIV’s strategic goals. |  |  |  |  |  |  |  |  |  |  |  |  |
| GPRA Goal |  |  | Project Objective |  |  |  |  |  |  |  |  |  |
| A. Project Alternatives: |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Enumeration of options and their projected costs. Include any obvious influence this may have on costs borne by other HHS organizations:  Option 1: Cost:  Option 2: Cost:  Option 3: Cost: |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Describe analysis of alternative options and identify any underlying assumptions. Provide estimates of complexity, costs, risks, i.e., rationale for “high,” “medium,” and “low” for each alternative.  Option 1: Briefly describe  Option 2: Briefly describe  Option 3: Briefly describe |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Decision: Financial Basis for Selecting the Project: Summarize the analysis of full life-cycle costs of ownership: results of cost/benefit analyses, including return on investment, and any tangible returns that benefit the Agency but are difficult to quantify. |  |  |  |  |  |  |  |  |  |  |  |  |
| B. Adherence to Architecture and Infrastructure Standards 1. Describe whether the project is compliant with the Department’s information technology architecture and technical infrastructure and, if not why not. 2. Identify standards for information exchange and resource sharing. 3. Demonstrate adherence to government-wide standards where applicable. 4. Identify use of commercial-off-the-shelf software (COTS) versus custom, justify custom components. |  |  |  |  |  |  |  |  |  |  |  |  |
| C. Describe the Security Plan for this investment |  |  |  |  |  |  |  |  |  |  |  |  |
| D. Timeline Information: Implementation Schedule: list milestones and dates |  |  |  |  |  |  |  |  |  |  |  |  |
| Fiscal year |  |  | Tasks |  |  |  |  |  |  |  |  |  |
| E. Acquisition Strategy |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Procurement Risk Management 2. Contract Vehicle 3. Summary of Acquisition Strategy 4. Type of Contract(s) Selected and Selection Rationale |  |  |  |  |  |  |  |  |  |  |  |  |
| F. Actual Performance and Variance from Approved Baseline (Original or Current): |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Variance in Cost 2. Variance in Schedule 3. Variance in Performance 4. Corrective Actions |  |  |  |  |  |  |  |  |  |  |  |  |
| G. Program Management |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Is there a program manager and contracting officer devoted to the project? Please name the person. |  |  |  |  |  |  |  |  | Yes |  | No |  |
| 2. Who is the contracting officer? |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Will an Integrated Project Team be established to assist with the Management of the project? If so, who will be on the team? |  |  |  |  |  |  |  |  | Yes |  | No |  |
| H. Please describe any Government Paperwork Elimination Act (GPEA) initiative |  |  |  |  |  |  |  |  |  |  |  |  |
| I certify the information presented is complete and accurate as of the date of my signature. |
| OPDIV CIO Certification Signature | Date |  |  |  |  |  |  |  |  |  |

# Figure C: HHS Capital Planning and Investment Control Checklist

This checklist is provided as guidance both for those preparing documents for ITIRB review and those conducting ITIRB reviews.  This is intended to be an illustrative but not exhaustive list of questions to answer. It does not attempt to specify a scoring and ranking system to be used in the evaluation process.

| (1) Business need statement |
| --- |
| Stage Decision Point DP | Project Title Selected | Provide a project title. |
| ALL | Project Owner Selected | Provide the name of the primary project owner who is responsible for the day-to day activities. |
| DP 2,3 | Sponsor of the Project | State the OPDIV and office that is the primary sponsor or advocate for the project. |
| ALL | Lead Component Selected | State the office or other component responsible for managing the project. (The project owner may or may not be the same person as the sponsor.) |
| ALL | Project Description | Describe the scope and nature for the project. Identify the business problem (administrative, programmatic, technological, or administrative savings). Describe how this investment will improve service or result in programmatic, technological, or administrative savings. Describe efficiencies and economies of scale. |
| ALL | Customers | List the organizations, components, or groups served by the effort. |
| ALL | Customer Needs | Identify the specific deficiency or need this project will fulfill and resulting profit or advancement that will be gained when the project is completed. |
| ALL | Authority/Mandate | State the legal or regulatory authority that entitles the agency to develop the project. Also state whether the project implements a current legislative requirement. |
| ALL | Type of Investment | State whether the project is major or non-major. |
| ALL | Impact of Not Funding | If this is a new investment, state the impact of failing to make the investment; i.e., what opportunity will be lost, or what mandated change will not be made. If a continuation of a prior year investment, state what customer system will be negatively affected if the project is terminated or the funding level is reduced. |
| ALL | Investment Size | Provide any information necessary to explain the funding requirements. |
| DP 2,3 | Period of Performance | State the total period of performance for the project. |
| DP 2,3 | Architectural Integration | Confirm that the technical strategy complies with the existing enterprise architecture. Describe any aspects that are not compatible and what steps are being taken to correct the deviation. List dependencies with other systems and projects. |
| (2) ROI and cost/benefit/alternatives analysis |
| DP 2,3 | Cost-Benefit Analysis | State the anticipated outcome of the project in quantifiable terms. Provide a formal Return on Investment (ROI) on the recommended option. |
| (3) &(5) Risk assessment and mitigation plan and economic sensitivity analysis |
| DP 2,3 | Risk Assessment | Provide a risk analysis that describes the factors or events that can jeopardize the success of the project. Describe any analysis of these dependencies and identify those events that pose the greatest risk to the success of the project. Describe the availability of specific resources (technology, staff, training, etc.). Provide a risk mitigation plan that addresses the way each risk will be dealt with if it occurs. |
| (4) Technical strategy and plan |
| ALL | Technical Strategy | Describe the overall technical strategy (e.g., mid-tier or mainframe, COTS, new system, etc.). |
| DP 2,3 | Technical Plan | State the basic or underlying technical assumptions regarding project implementation. State the specific technical approaches and methodologies that will support your solution. |
| (6) Performance measurement plan |
| DP 2,3 | Performance Measures | Explain how the progress of the investment, while being implemented, will be measured. State the final anticipated outcome or level of performance after implementation. For each performance measure, state the information collection method and any estimated or anticipated results. |
| (7) Spending and procurement plan |
| DP 2,3 | Detail Information | Estimate the funding requirements by cost category and fiscal year. These categories include hardware, software, telecommunications, systems development, support and maintenance, staffing travel, training. |
| DP 2,3 | Staffing | List the types of staff and the number of hours that they will devote to this project for the life of the project. Include both government staff and contractor staff. |
| (8) Project plan, schedule and work breakdown schedule |
| DP 2,3 | Project Life Cycle Phases | Identify the specific phases of the project. Describe the modularity of the project. Enumerate the discrete activities and points of success that exist within the project. State the activities within each phase of the project. |

# Appendix A: Legislative Requirements and Guidance for Capital Planning and Investment Controls

The requirements and guidance for capital planning and investment control include:

(1)	The Clinger-Cohen Act (CCA) (includes the Information Technology Management Reform Act and the Federal Acquisition Reform Act).  The CCA requires the head of each executive agency to design and implement a process for maximizing the value and assessing and managing the risk of information technology (IT) acquisitions, development of an information technology architecture (ITA), and designation of Chief Information Officers (CIOs).

(2)	OMB Circular A-130, Management of Information Resources. This provides uniform information on information resources management (IRM)  policies required by the Paperwork Reduction Act, in Section 8(b).The term “major” information system, means an information system that requires special management attention because of its importance to an agency mission; its high development, operating or maintenance costs; or its significant role in the administration of agency programs.

(3)	OMB Memorandum 97-02, Funding Information Systems Investments.  This guidance memorandum, which is commonly referred to as the “Raines’ Rules,” establishes eight decision rules that OMB uses to evaluate major information system investments proposed for submission in the President’s budget.

(4)	The Government Performance and Results Act (GPRA). The GPRA requires agencies to set goals, measure performance, and report on their accomplishments, and require IT investments to directly support the accomplishment of these goals.

(5)	OMB Circular A-76, Performance of Commercial Activities.  The A-76 establishes policy regarding the performance of commercial activities and implements the statutory requirements of the Federal Activities Inventory Reform Act of 1998.  The supplement to this circular sets forth the procedures for determining whether commercial activities should be performed under contract with commercial sources or in- house, using Government facilities and personnel.

(6)	OMB Circular A-11. Circular A-11 consists of Part 1, entitled “Preparation and Submission of Budget Estimates,” Part 2, “Preparation and Submission of Strategic Plans and Annual Performance Reports,” and Part 3, “Planning, Budgeting, and Acquisition of Capital Assets.”  A supplement to Part 3, “Capital Programming Guide,” is also included.

(7)	OMB Circular A-127, Financial Management Systems. CircularA-127 prescribes policies and standards for executive departments and agencies to follow in developing, operating, evaluating, and reporting on financial management systems.

(8)	The Joint Financial Management Improvement Program (JFMIP).  The JFMIP encourages and promotes the government-wide sharing and exchange of information concerning good financial management techniques and practices.  Included are financial management events and training calendars, listings of best shared practices, project reports, news, announcements, and meeting minutes.

(9)	The Paperwork Reduction Act (PRA). The PRA requires Federal agencies to define program information needs and develop strategies, systems and capabilities to meet those needs; the PRA also requires the development of a five-year strategic plan.

(10)	The Chief Financial Officers (CFO) Act.  The purpose of the CFO Act is to bring more effective general and financial management practices to the Federal Government, and to improve accounting, financial management, and internal controls, and to provide for complete, reliable, timely, and consistent financial information.

(11)	OMB Circular A-94, Guidelines and Discount Rates for Benefit-Cost Analysis of Federal Programs.  A-94 provides guidance for conducting cost-benefit and effectiveness analyses, and provides guidance on the discount rates to be used in evaluating Federal programs whose costs and benefits are distributed over time.

- The Workforce Investment Act of 1998.  The Workforce Investment Act revised Section 508 of the Rehabilitation Act of 1973 by requiring Federal agencies to ensure that the electronic and information technologies used in federal programs are accessible to individuals with disabilities to the same extent as those without disabilities.  The Act strengthens Section 508 by imposing strict requirements for any electronic and information technology developed, maintained, procured, or used by Federal agencies. Section 508 also establishes mechanisms for enforcing these strict requirements through civil actions or administrative complaints.

- The Federal Acquisition Streamlining Act of 1994 (FASA) requires OMB to report on the cost, schedule and performance goals for asset acquisitions and how well agencies are meeting their goals.

- Internal Revenue Service Model Information Technology Privacy Impact Assessment, adopted by Federal CIO Council as model policy.